## Sheet1
See column descriptions in other tab
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | As a user, I want to log in using my student email and password. | 2 | Low | To Do | 3
2 | As a user, I want to log in using my Google account. | 2 | High | To Do | 2
3 | As a user, I want to log out of my account. | 2 | High | To Do | 1
4 | As a user, I want to provide my home address. | 2 | High | To Do | 2
5 | As a user, I want to update my home address. | 3 | Medium | To Do | 2
6 | As a user, I want to change my password. | 2 | Low | To Do | 2
7 | As a user, I want to edit my driving schedule and specify when I can offer rides to and from campus. | 1 | High | To Do | 6
8 | As a user, I want to update my vehicle details. | 2 | Low | To Do | 2
9 | As a user, I want to submit a carpool request. | 1 | High | To Do | 3
10 | As a user, I want to search for a list of available carpool options based on my location and class schedule. | 1 | High | To Do | 8
11 | As a user, I want to report other users who are unreachable. | 3 | Low | To Do | 3
12 | As a user, I want to send a tip to my driver via PayPal. | 4 | Low | To Do | 4
13 | As a user, I want to be able to view past rides, both as a driver and a passenger. | 4 | Low | To Do | 4
14 | As a user, I want to view profile information of other users. | 1 | Medium | To Do | 2
15 | As a driver, I want to set the maximum number of passengers in my car. | 4 | Medium | To Do | 3
16 | As a user, I want to be able to decline ride requests sent to me | 2 | Medium | To Do | 2
17 | As a driver, I want to recieve a notification for carpool requests | 2 | Medium | To Do | 3
18 | As a user, I want to send/recive messages from any student i've been paired with | 2 | Medium | To Do | 5
19 | As a driver, I want to have the option to set a price request from passengers (tips). | 4 | Low | To Do | 3
20 | As a user, I would like to write feedback about a user I have carpooled with before | 3 | Low | To Do | 2
21 | As a user, I want access to a feedback/support system in case there are any issues. | 4 | Low | To Do | 2
22 | As a driver, I want to set preferences for who I am willing to drive (gender/smoking preferences, etc.). | 4 | Low | To Do | 4
23 | As a driver, I would like to share my phone number with students I carpool with to streamline communication. | 2 | Medium | To Do | 1

## Description of Columns
ID: unique # for each story * Story: Contains the user stories (one story per row) in priority order ▪ Formatted as “As a <user role>, I need to <feature needed> because of <benefit>. o Sprint: The story’s sprint number (when it gets implemented) o Story Priority: H (high), M (medium), L (low) o Story Status: W (waiting), IP (in progress), T (testing), D (done) o Story Points: Number of story points gives an indication of the difficulty of the story’s development and testing as well as possibly an estimate of the number of hours to design, implement, and test the story.