## Project Backlog (User stories)
Item description | Story ID | User story | points | Priority | Recommended subtasks
User account 1 | 1 | As a user I want to be able to create an acount so that I can use the application | 4
| 2 | As a user I want to be able to log in to my account, so that I can access my account
| 3 | As a user I want to view a homescreen when I log in, so that I can navigate to other parts of the application
| 4 | As a user I want to be able to verify my UMaine ID card, so I can access the full suite of application features
| 5 | As a user I want to be able to log out of my account, to maintain my account security
Profile information | 6 | As a user I want a profile page where I can see my profile
| 7 | As a user I want to be able to change my password, so that I can maintain my account security
| 8 | As a user I want to be able to provide my schedule, so that it is visible to other users
| 9 | As a User I want to be able to provide vehicle details so that they are visible to other users
| 10 | As a user I want to be able to set my maximum number of passengers, so I don't end up with more requests than I can take
| 11 | As a user I want to be able to provide my home address so that other users will know my area of operation
| 12 | As a user I want to be able to provide rideshare partner preferences, so that I'm not matched with someone I'm uncomfortble with
User Interactions | 13 | As a user I want to be able to view other peoples profiles, so that I know more about them
| 14 | As a user I want to be able to search other users based schedule and area so I can try to match with someone
| 15 | As a user I want to be able to submit carpool requests to people who match my schedule
| 16 | As a user I want to be recieve notifications when people are requesting a ride from me
| 17 | As a user I want to be able to decline or accept rideshare requests
| 18 | As a user I want to be able to share my phone number so that other users can get in touch with me more easily
Feedback system | 19 | As a user I want to be able to report users for various reasons
| 20 | As a user I want to be able to provide feedback on a previous rideshare partner
Profile information pt2 | 21 | A a user I want to be able to view past rideshare events associated with my account, so I know who I've shared a ride with and when
| 22 | As a user I want to be able to view rideshare feedback on my account
user interaction part 2 | 23 | As a user I want to be able to tip my driver
| 24 | as a user I want to be able to exchange DMs with the user I'm matched with

## Project Backlog
Story ID | Task description | # | Subtask description | Story points | Might not be possible currently | Already done
1 | Make a page where users can sign up for an account, as according to wireframes | 1.1 | Create a page dedicated to account creation | 1
|  | 1.2 | have a "Welcome to Bearpool" banner | 1
|  | 1.3 | Have input fields for "Email" "Password" "Confirm Password" | 1
|  | 1.4 | Have a Signup Button | 1
2 | Create a login screen as according to the wireframe | 2.1 | Create a page dedicated to logging into an account | 1
|  | 2.2 | Have a banner which says "Welcome to Bearpool" | 1
|  | 2.3 | Have input fields for "Email" and "Password" | 1
|  | 2.4 | Have a "Login" button to confirm | 1
|  | 2.5 | Have a "Create an account" button linking to the account creation page | 1
3 | Create a Homescreen as according to the wireframe | 3.1 | Create Wireframe for Homescreen | 1
|  | 3.2 | (preliminary) have a button linking to user profile | 1
|  | 3.3 | (preliminary) have a button for 'find a ride' linking to nothing for now | 1
|  | 3.4 | (preliminary) have a button for 'logging out' | 1
4 | Implement a page where in the future we can check IDs | 4.1 | Review wireframe for ID card varification | 1
|  | 4.2 | create a screen for an ID scanner | 1
|  | 4.3 | create a scanner | 1
5 | Implement a log out feature | 5.1 | Create a log out button on the homepage | 1
|  | 5.2 | Have the button take you to the login page | 1
|  | 5.3 | Have the button remove data from the app? | 1
6 | Create a profile page | 6.1 | create a page dedicated to profile information | 1
|  | 6.2 | create a button indicating an edit mode | 1
7 | Create a way for a user to change their password once it has been implemented | 7.1 | create a way to edit a password ( or give the illusion of editing a password) based off of the edit button on the profile page | 1
8 | Create a way for the user's schedule to be displayed, and a way for them to change it | 8.1 | change the profile page such that it displays a place for a schedule | 1
|  | 8.2 | Make a way to edit the user's schedule via the edit button on the profile page | 1
|  | 8.3 | create a way for this information to be accessed dynamicaly later | 1
9 | Create a way for the user's vehicle info to be displayed on profile, and for them to change it(probably just plain text) | 9.1 | create an entry on the prfile page to display vehicle information | 1
|  | 9.2 | Create a way for the user to change the information through the edit menu | 1
10 | create a way for the user to provide the maximum number of passengers they can transport | 10.1 | create a place on the profile for maximum occupancy | 1
|  | 10.2 | create a way for maximum occupancy to be edited by the user | 1
|  | 10.3 | create a way for the application to access this information dynamically later | 1
11 | Create a way for the user to provide their home address | 11.1 | create a place on the profile to provide home address
|  | 11.2 | create a way for the user to edit their home address
12 | create a way for the user to communicate their rideshare preferences | 12.1 | create a place for the user to provide rideshare preferences
|  | 12.2 | create a way for the user to edit their rideshare preferences

## Sprint backlog
Story ID | User Story | Task ID | Story Tasks | Deliverable number | Sprint Goal | Story Type | Story Points | Story Points Completed | Assignee | Might not be possible currently | Already done | outstanding
1 | Create user stories | 1.1 | Create initial list of user stories | 0 | establish initial documentation | D | 1 | 1 | Knox Brown
2 | Competitor Research | 2.1 | Produce information on BBOE |  |  | D | 1 | 1 | Kledis Zaimi
|  | 2.2 | Produce information on Ride share Lyft |  |  | D | 1 | 1 | Abhilash Durgam
|  | 2.3 | Produce information on Ride share Uber |  |  | D | 1 | 1 | David Neufeld
3 | Preliminary project description | 3.1 | Produce proto projecet description |  |  | D | 1 | 1 | Knox Brown
4 | SRS Nonfucntional requirements | 4.1 | Create non-functional requirements document | 1 | Respond to deliverable 0 grading and create more documentation | D | 1 | 1 | Kledis Zaimi
|  | 4.2 | Create non-functional requirements document |  |  | D | 1 | 1 | David Neufeld
5 | Create basis for github content | 5.1 | add code and scripts to Github, create github presence |  |  | D | 1 | 1 | All members
6 | Create Kanban | 6.1 | create initial Kanban board |  |  | D | 1 | 1 | Abhilash Durgam
7 | Sprint review 1 | 7.1 | write sprint review for previous sprint |  |  | D | 1 | 1 | Abhilash Durgam
8 | Sprint Backlog 1 | 8.1 | Create sprint backlog document |  |  | D | 1 | 1 | Kledis Zaimi
9 | Update project description document | 9.1 | Respond to comments on project description document from last sprint |  |  | D | 1 | 1 | Quinn Knowles
10 | Product Backlog | 10.1 | Create product backlog |  |  | D | 1 | 1 | David Neufeld
11 | Create SRS Functional requirement document | 11.1 | Create Functional requirements |  |  | D | 1 | 1 | Kledis Zaimi
|  | 11.2 | Create functional requirements |  |  | D | 1 | 1 | David Neufeld
12 | Update user story document | 12.1 | Edit the user story document |  |  | D | 1 | 1 | Knox Brown
13 | Sprint backlog 2 | 13.1 | Create sprint backlog for deliverable 2 | 2 |  | D | 1 | 1 | Quinn Knowles
14 | Address SRS comments from deliverable 1 | 14.1 | Edit SRS as needed |  |  | D | 1 | 1 | Kledis Zaimi
15 | Create new version of the application | 15.1 | Create initial stages for the application |  |  | NF | 1 | 1 | Abhilash Durgam
16 | Sprint review 2 | 16.1 | write sprint review for previous sprint |  |  | D | 1 | 1 | David Neufeld
17 | Use case descriptions | 17.1 | Write use case description documents |  |  | D | 1 | 1 | Quinn Knowles
|  | 17.2 | write use case description documents |  |  | D | 1 | 1 | David Neufeld
|  | 17.3 | write use case description documents |  |  | D | 1 | 1 | Abhilash Durgam
|  | 17.4 | write use case description documents |  |  | D | 1 | 1 | Knox Brown
|  | 17.5 | write use case description documents |  |  | D | 1 | 1 | Kledis Zaimi
|  | 17.6 | Edit and proof read use case descriptions |  |  | D | 1 | 1 | Knox Brown
18 | Create usecase diagrams | 18.1 | Create 2 usecase diagrams |  |  | D | 1 | 1 | Kledis Zaimi
19 | Architecture Design | 19.1 | Create MVC architecture desgin |  |  | D | 1 | 1 | Knox Brown
20 | kanban 2 | 20.1 | Update kanban board with progress |  |  | D | 1 | 1 | Kledis Zaimi
21 | Product backlog 2 | 21.1 | Update product backlog |  |  | D | 1 | 1 | David Neufeld
22 | UI Mockups | 22.1 | Create UI Mockups | 3 |  | D | 1 | 1 | Tiffany Ha
|  | 22.2 | Create UI Mockups |  |  | D | 1 | 1 | John Kearney
23 | Analysis Sequence diagrams | 23.1 | Create Analysis diagrams based on use case descriptions |  |  | D | 1 |  | Quinn Knowles
|  | 23.2 | Create Analysis diagrams based on use case descriptions |  |  | D | 1 | 1 | Knox Brown
|  | 23.3 | Create Analysis diagrams based on use case descriptions |  |  | D | 1 | 1 | Kledis Zaimi
|  | 23.4 | Create Analysis diagrams based on use case descriptions |  |  | D | 1 | 1 | David Neufeld
|  | 23.5 | Create Analysis diagrams based on use case descriptions |  |  | D | 1 | 1 | Abhilash Durgam
24 | Product backlog overhaul | 24.1 | Reorder product backlog |  |  | D | 1 | 1 | Quinn Knowles
25 | Sprint backlog 3 | 25.1 | update sprint backlog |  |  | D | 1 | 1 | Quinn Knowles
26 | Usability testing revisions | 26.1 | Revise usability testing |  |  | D | 1 | 1 | Tiffany Ha
|  | 26.2 | revise usability testing |  |  | D | 1 | 1 | John Kearney
27 | Product backlog item: Home screen | 27.1 | Create Wireframe for Homescreen |  |  | D | 1 | 1 | Abhilash Durgam
|  | 27.2 | (preliminary) have a button linking to user profile |  |  | NF | 1 |  | Abhilash Durgam
|  | 27.3 | (preliminary) have a button for 'find a ride' linking to nothing for now |  |  | NF | 1 | 1 | Abhilash Durgam
|  | 27.4 | (preliminary) have a button for 'logging out' |  |  | NF | 1 |  | Abhilash Durgam
28 | Kanban 3 | 28.1 | Update kanban board with progress | 4 | Implement basic features | D | 1
29 | Sprint backlog 4 | 29.1 | Update sprint backlog |  |  | D | 1 |  | Quinn Knowles
30 | Product backlog 4 | 30.1 | Update product backlog |  |  | D | 1 |  | Quinn Knowles
31 | Make a page where users can sign up for an account, as according to wireframes | 31.1 | Create a page dedicated to account creation |  |  |  | 1
|  | 31.2 | have a "Welcome to Bearpool" banner |  |  |  | 1
|  | 31.3 | Have input fields for "Email" "Password" "Confirm Password" |  |  |  | 1
|  | 31.4 | Have a Signup Button |  |  |  | 1
32 | Create a login screen as according to the wireframe | 32.1 | Create a page dedicated to logging into an account |  |  |  | 1
|  | 32.2 | Have a banner which says "Welcome to Bearpool" |  |  |  | 1
|  | 32.3 | Have input fields for "Email" and "Password" |  |  |  | 1
|  | 32.4 | Have a "Login" button to confirm |  |  |  | 1
|  | 32.5 | Have a "Create an account" button linking to the account creation page |  |  |  | 1
33 | Create a profile page | 33.1 | create a page dedicated to profile information |  |  | NF | 1
|  | 33.2 | create a button indicating an edit mode |  |  |  | 1
34 | Create a way for a user to change their password once it has been implemented | 34.1 | create a way to edit a password ( or give the illusion of editing a password) based off of the edit button on the profile page |  |  |  | 1
35 | Create a way for the user's schedule to be displayed, and a way for them to change it | 35.1 | change the profile page such that it displays a place for a schedule |  |  |  | 1
|  | 35.2 | Make a way to edit the user's schedule via the edit button on the profile page |  |  |  | 1
|  | 35.3 | create a way for this information to be accessed dynamicaly later |  |  |  | 1
36 | Create a way for the user's vehicle info to be displayed on profile, and for them to change it(probably just plain text) | 36.1 | create an entry on the prfile page to display vehicle information |  |  |  | 1
|  | 36.2 | Create a way for the user to change the information through the edit menu |  |  |  | 1
37 | create a way for the user to provide the maximum number of passengers they can transport | 37.1 | create a place on the profile for maximum occupancy |  |  |  | 1
|  | 37.2 | create a way for maximum occupancy to be edited by the user |  |  |  | 1
|  | 37.3 | create a way for the application to access this information dynamically later |  |  |  | 1